## How to use
CNC Job Shop Production Planning Template
Free template from KeshRaghTech (keshraghtech.com). Built for CNC job shops: plan by machine, release only ready jobs, plan the bottleneck first.
Colour legend
Yellow cells, blue text: you fill these in.
Grey cells: calculated by formulas. Don't type over them.
All example jobs, machines and times are made up. Overwrite them with your own.
Set up once
1. Machines tab: list every machine or work centre with its shifts, hours and a realistic availability % (start with 80% if unsure).
2. Jobs tab: one row per open order: due date, and Yes/No for material, program, tooling and drawing.
3. Operations tab: each job's operations in order, with machine, setup hours and run minutes per piece.
Every morning (15 minutes)
1. Update yesterday: mark finished operations Done, and finished jobs Done.
2. Machines tab: check the busiest machine (shown under the table). Any Load % in red means the open work does not fit this week.
3. Jobs tab: release only jobs marked Ready, in priority order. Fix anything marked "Released before ready".
4. Daily Plan tab: plan the busiest machine first, then the machines that feed it. Print it for the floor.
5. One plan, one owner: keep a single copy of this file and let one person change priorities.
Before the shift ends (5 minutes)
Mark each planned line Done = Yes or No, and pick a reason for every No. After a week, the reasons summary shows what really breaks your plan.
When Excel is no longer enough
If several people need to update the plan at once, the file is out of date by mid-morning, or you keep chasing the floor for status, the plan has outgrown a spreadsheet.
Read: Production Planning in Excel for CNC Job Shops - https://keshraghtech.com/operations-insights/production-planning-in-excel

## Machines
Machines & capacity
One row per machine or work centre. Yellow = you fill in, grey = calculated. Load counts every operation that is not Done, so you can see if the open orders fit before you promise a date.
Machine / work centre | Shifts per day | Hours per shift | Availability % | Available hrs / day | Working days this week | Available hrs / week | Open load (hrs) | Load % of week | Days of work waiting
CNC Lathe 1 | 2 | 8 | 85% |  | 6
CNC Lathe 2 | 2 | 8 | 85% |  | 6
VMC 1 | 2 | 8 | 80% |  | 6
VMC 2 | 1 | 8 | 80% |  | 6
HMC 1 | 2 | 8 | 80% |  | 6
Cylindrical Grinder | 1 | 8 | 85% |  | 6
Deburr & Finishing | 1 | 8 | 90% |  | 6
Final Inspection | 1 | 8 | 90% |  | 6
Busiest machine (your likely bottleneck):
Plan this machine first. Every other machine should feed it, not run ahead of it.
Load % above 100% (red) = the open work does not fit this week: re-plan or tell the customer now, not on the due date.
Note on D5: Share of shift time the machine really cuts, after breaks, setups, waiting and breakdowns. Example values: measure your own for a week.
Note on F5: Example assumes a 6-day week. Change per machine if needed.

## Jobs
Jobs (open orders)
One row per job. A job is "Ready" only when material, program, tooling and drawing are all confirmed. Release only Ready jobs, in priority order (1 = first).
Job no | Customer | Part / description | Qty | Due date | Material ready | Program ready | Tooling & fixture ready | Drawing / QC plan ready | Ready to release? | Status | Priority (1 = first) | Days to due | Hours left | Warning
J-1041 | Customer A | Hydraulic valve body | 40 |  | Yes | Yes | Yes | Yes |  | In progress | 1
J-1042 | Customer B | Pump shaft | 120 |  | Yes | Yes | Yes | Yes |  | Released | 2
J-1043 | Customer A | Flange adaptor | 60 |  | Yes | Yes | No | Yes |  | Not released | 4
J-1044 | Customer C | Gear blank | 200 |  | Yes | Yes | Yes | Yes |  | Released | 3
J-1045 | Customer D | Mounting bracket | 80 |  | No | Yes | Yes | Yes |  | Not released | 6
J-1046 | Customer B | Bearing housing | 30 |  | Yes | No | Yes | Yes |  | Released | 5
J-1047 | Customer E | Spacer ring | 300 |  | Yes | Yes | Yes | Yes |  | Not released | 7
J-1048 | Customer C | Coupling hub | 50 |  | Yes | Yes | Yes | No |  | On hold | 8
Formulas:
Days to due = IF(OR([Job no]="",[Due date]=""),"",[Due date]-TODAY())
Note on E5: Example jobs are made up, and their due dates are set to a few days from today. Overwrite them with your own dates.

## Operations
Operations (routing)
One row per operation of each job, in order. Total hours = setup + qty x run time. Mark an operation Done when it is finished: that is what keeps the machine load on the Machines tab true.
Job no | Op no | Operation | Machine | Qty | Setup hrs | Run min / piece | Total hrs | Status | Job due date | Job priority | Key (job-op)
J-1041 | 10 | Turning | CNC Lathe 1 |  | 1.5 | 6 |  | Done
J-1041 | 20 | Milling - ports | VMC 1 |  | 2 | 14 |  | Running
J-1041 | 30 | Deburr | Deburr & Finishing |  | 0.3 | 3 |  | Waiting
J-1041 | 40 | Inspection | Final Inspection |  | 0.2 | 4 |  | Waiting
J-1042 | 10 | Turning | CNC Lathe 2 |  | 1 | 4 |  | Running
J-1042 | 20 | Keyway milling | VMC 2 |  | 1.5 | 3 |  | Waiting
J-1042 | 30 | Grinding | Cylindrical Grinder |  | 1 | 5 |  | Waiting
J-1042 | 40 | Inspection | Final Inspection |  | 0.2 | 1.5 |  | Waiting
J-1043 | 10 | Turning | CNC Lathe 1 |  | 1 | 5 |  | Waiting
J-1043 | 20 | Drilling pattern | VMC 1 |  | 1.5 | 6 |  | Waiting
J-1043 | 30 | Inspection | Final Inspection |  | 0.2 | 2 |  | Waiting
J-1044 | 10 | Turning | CNC Lathe 2 |  | 1 | 3 |  | Waiting
J-1044 | 20 | Face milling | VMC 1 |  | 1 | 4 |  | Waiting
J-1044 | 30 | Inspection | Final Inspection |  | 0.2 | 1 |  | Waiting
J-1045 | 10 | Milling | HMC 1 |  | 2.5 | 9 |  | Waiting
J-1045 | 20 | Deburr | Deburr & Finishing |  | 0.3 | 2 |  | Waiting
J-1046 | 10 | Turning | CNC Lathe 1 |  | 1.5 | 8 |  | Waiting
J-1046 | 20 | Boring & milling | VMC 1 |  | 2.5 | 18 |  | Waiting
J-1046 | 30 | Inspection | Final Inspection |  | 0.3 | 5 |  | Waiting
J-1047 | 10 | Turning | CNC Lathe 2 |  | 0.5 | 1.5 |  | Waiting
J-1047 | 20 | Inspection | Final Inspection |  | 0.2 | 0.5 |  | Waiting
J-1048 | 10 | Turning | CNC Lathe 1 |  | 1 | 4 |  | Waiting
J-1048 | 20 | Spline milling | VMC 1 |  | 2 | 12 |  | Waiting

## Daily Plan
Daily plan (print for the morning meeting)
Plan the busiest machine first, then the others to feed it. Before the shift ends, mark each line Done = Yes / No and pick a reason for every No. The reasons summary below shows what to fix first.
Date:
Machine | Seq | Job no | Op no | Operation | Planned hrs | Job due | Done? | If No: reason | Notes
VMC 1 | 1 | J-1041 | 20 |  |  |  | Yes
VMC 1 | 2 | J-1044 | 20 |  |  |  | No | Previous operation late
CNC Lathe 2 | 1 | J-1042 | 10 |  |  |  | Yes
CNC Lathe 2 | 2 | J-1044 | 10 |  |  |  | Yes
CNC Lathe 1 | 1 | J-1046 | 10 |  |  |  | No | Program not ready
VMC 2 | 1 | J-1042 | 20
Plan achieved |  |  | of planned lines done (lines without Yes/No are not counted)
Why planned work was not done
The reason with the highest count is your first thing to fix: it is breaking the plan more than anything else.

## Lists (hidden)
Yes / No | Job status | Operation status | Reason not done
Yes | Not released | Waiting | Material not ready
No | Released | Running | Program not ready
| In progress | Done | Tool / fixture not ready
| On hold |  | Machine breakdown
| Done |  | Operator not available
QC hold / rework
Priority changed
Setup took longer
Previous operation late